Week 3 — Stakeholder Management & Delivery

Project: “CoffeeHolic”- Coffee Shop Management System

Week 1 feature carried into this task: Counter Ordering & Payment (the in-store POS flow)

# Jira Backlog Setup Guide

## Step 1: Create Free Jira Board

- Go to https://www.atlassian.com/software/jira/free

- Sign up with your student email (the free tier covers up to 10 users, which is more than a 4-person team needs)

- Create a new Scrum project called "Coffeeholic Team"

- Set sprint duration to 2 weeks

- Add the four epics below before you add any stories, otherwise Jira will not let you link them

## Step 2: Epics

Epic-001: Counter Ordering & Payment

A barista can build a customer’s order at the till, take payment, and hand back a receipt without touching a calculator or a paper docket.

Epic-002: Menu & Stock Control

The owner can change what is sold and for how much, and the system keeps a running count of beans, milk and cups as orders go through.

Epic-003: Customer Loyalty & Order Ahead

Regulars can collect and spend stamps, and eventually order from their phone before they walk in.

Epic-004: Staff Rostering & Daily Reporting

The owner can roster shifts for the week and see what the shop actually took at the end of a trading day.

## Step 3: User Stories (Broken Down from Epics)

| Story ID | Epic | Title | Priority | Points | Status |
| --- | --- | --- | --- | --- | --- |
| CS-001 | Epic-001 | Build an order at the till (items + modifiers) | High | 8 | To Do |
| CS-002 | Epic-001 | Take payment (cash or card) and issue receipt | High | 8 | To Do |
| CS-003 | Epic-001 | Push confirmed order to the barista queue screen | High | 5 | To Do |
| CS-004 | Epic-002 | Owner adds, edits and retires menu items | High | 5 | To Do |
| CS-005 | Epic-002 | Deduct ingredients from stock when a drink is sold | Medium | 8 | To Do |
| CS-006 | Epic-002 | Low-stock warning on the owner dashboard | Medium | 3 | To Do |
| CS-007 | Epic-003 | Loyalty stamps: earn on purchase, redeem on 10th | Medium | 5 | To Do |
| CS-008 | Epic-003 | Order ahead from a phone and pay on pickup | Low | 13 | To Do |
| CS-009 | Epic-004 | Roster staff across a trading week | Low | 8 | To Do |
| CS-010 | Epic-004 | End-of-day sales summary and cash reconciliation | Medium | 5 | To Do |

Total backlog: 68 points.

## Step 4: Priority Rationale (MoSCoW Method)

| Priority | Stories | Reasoning |
| --- | --- | --- |
| Must Have | CS-001, CS-002, CS-003, CS-004 | A café cannot trade without taking an order, charging for it, and telling the barista what to make. CS-004 is in here because the till has nothing to sell until someone loads the menu. |
| Should Have | CS-005, CS-006, CS-007, CS-010 | These save the owner real money and time, but the shop can open without them. Stock can be counted by hand for a few weeks. |
| Could Have | CS-008, CS-009 | Order-ahead is the biggest story in the backlog and needs a payment gateway plus a second app surface. Rostering can live in a spreadsheet for now. |
| Won’t Have (this release) | Table service, supplier auto-ordering, accounting software integration, multi-store support | Out of scope. The client runs one shop and does the books with an external bookkeeper. |

A note on CS-005. It sits in Should Have rather than Must Have, which surprised the owner during backlog review. The argument for holding it back is that stock deduction depends on a recipe model (how many grams of beans in a large flat white), and that modelling work would swallow most of Sprint 1 on its own. It has been logged as a decision, not a deferral, so it does not come back as a scope argument in Sprint 2.

## Step 5: Sprint 1 Planning — Backlog Board Layout

Sprint 1 Goal: "A barista can take a counter order, charge for it, and have it appear on the coffee queue screen."

Sprint 1 Capacity: 2 weeks, 4 team members, roughly 30 story points

Sprint 1 Selected Stories:

- CS-001: Build an order at the till (8 pts)

- CS-002: Take payment and issue receipt (8 pts)

- CS-003: Push order to barista queue screen (5 pts)

- CS-004: Owner manages menu items (5 pts)

- Committed total: 26 points

- CS-006 (3 pts) is held as a stretch pull if the team clears the commitment by day 8

Sprint 1 Board Columns:

[Backlog]  →  [To Do]  →  [In Progress]  →  [In Review]  →  [Done]

## Acceptance Criteria for Sprint 1 Stories

### CS-001 — Build an order at the till

- Barista can add multiple items to one order

- Each coffee item accepts size, milk type and extra shots as modifiers

- Modifiers that cost money (oat milk, extra shot) update the order total as they are selected

- Barista can remove a line or clear the whole order before payment

- Order total shows GST-inclusive pricing

### CS-002 — Take payment and issue receipt

- Barista selects cash or card

- Cash path calculates change owed from the amount tendered

- Card path sends the total to the EFTPOS terminal and waits for an approved or declined response

- A declined payment returns to the order screen with the order intact

- Receipt is printed or emailed, and carries the ABN, date, order number and GST line

### CS-003 — Push the order to the barista queue screen

- Paid orders appear on the queue screen within 2 seconds

- Each ticket shows order number, drinks, modifiers and time waiting

- Barista can mark a ticket as made, which clears it from the queue

- Screen survives a page refresh without losing the queue

### CS-004 — Owner manages menu items

- Owner can create an item with a name, category, price and available modifiers

- Owner can change a price, and the change applies to new orders only

- Retiring an item hides it from the till but keeps it in past order history

- Only an account with the owner role can reach this screen

# 15-Minute Mock Sprint Planning Script

Role: You are the Product Owner / BA facilitating Sprint Planning

Audience: Your development team (or record this for your assignment)

Duration: 15 minutes

## Minute 0–2: Opening & Sprint Goal

"Morning everyone. This is Sprint 1 Planning for BrewBook. Our goal for the next two weeks is one sentence: a barista can take a counter order, charge for it, and have it show up on the coffee queue screen.

I want to be clear about why that is the goal and not something bigger. We met the owner last Thursday. She said the thing that actually hurts on a Saturday morning is the queue, not the reporting. So the sprint is aimed at the till and nothing else.

Any questions on the goal before we go into the backlog?"

## Minute 2–5: Review Backlog & Priorities

"Here is what I have pulled in, based on our 30-point capacity and the dependencies between these stories.

1. CS-004 — Menu management (5 pts). This one goes first even though it is not the most exciting. The till has nothing to display until the menu exists in the database.

2. CS-001 — Build an order at the till (8 pts). Items plus modifiers. The modifiers are where the complexity lives.

3. CS-002 — Payment and receipt (8 pts). Cash and card. There is an external dependency here and I want to talk about it.

4. CS-003 — Barista queue screen (5 pts). The output end of the flow.

That is 26 committed. CS-006, the low-stock warning, is 3 points and sits as a stretch if we are ahead by day 8. I would rather under-commit and pull extra in than blow the sprint.

Does 26 feel realistic to the four of you?"

## Minute 5–8: Story Discussion & Clarification

"Let’s dig into the two I am least sure about.

CS-001, the modifiers. A large oat flat white with an extra shot is one drink with three modifiers, and two of them change the price. Is that one story at 8 points, or do we split it into a plain item picker and a separate modifiers story? My instinct is to keep it whole because a half-built till is not demoable, but I will take the team’s view.

[Wait for team response]

CS-002, the card payment. We are not writing our own payment processing. The shop already has a Tyro terminal. The question for the sprint is whether we integrate with the terminal API now, or whether we ship a manual card mode where the barista taps the amount into the terminal by hand and confirms in our app. Manual mode is maybe 3 points. Real integration is 8 on its own and depends on merchant credentials we do not have yet.

[Wait for team response]

I will flag now that I have emailed the owner about those credentials and have not heard back. If nothing lands by Wednesday, we build manual mode and raise integration as its own story in Sprint 2.

One more thing on CS-003. The shop’s internet drops out. The owner mentioned it twice. Do we need the queue screen to keep working offline in Sprint 1, or can that wait? I think it waits, but somebody should write it down as a risk.

[Wait for team response]

Anything else before we commit?"

## Minute 8–11: Task Breakdown & Assignment

"Breaking CS-001 into tasks:

Task 1.1: Order and OrderLine entities, plus the modifier price model — Dev Lead

Task 1.2: Till screen UI with category tabs and the running total — Frontend Dev

Task 1.3: Modifier selection logic and price recalculation — Backend Dev

Task 1.4: Unit tests for order total maths, including GST rounding — Tester

CS-002 tasks:

Task 2.1: Payment entity and the cash change calculation

Task 2.2: Manual card mode with an approved or declined outcome

Task 2.3: Receipt template with ABN, GST line and order number

Task 2.4: Tests for the declined-payment path, because that is the one that loses money if it is wrong

CS-004 goes to the Frontend Dev in the first three days so the rest of us have data to work against. CS-003 starts on day 6, after CS-001 is in review.

Does everyone have enough to start Monday?"

## Minute 11–13: Definition of Done (DoD) Review

"Our Definition of Done for every story this sprint:

1. Code written and peer-reviewed by someone who did not write it

2. Unit tests pass, minimum 80% coverage on anything that touches money

3. Acceptance criteria verified by the Tester against the story, not against the code

4. BA has run the feature once as a barista would run it

5. No open critical or high bugs

6. Any decision that changed the story is written into the Jira comment thread

Point 4 is new this sprint. Last time we accepted a feature that passed every test and was unusable at speed. Everyone happy with this as the standard?"

## Minute 13–15: Commitment & Close

"Right. Do we commit to 26 points for Sprint 1? Show of hands.

[Team votes]

Committed, and the backlog is locked. Standups at 9:00, kept to 10 minutes. Sprint review is Friday week at 2pm and the owner is coming in for it, so we demo on the real till hardware, not on a laptop.

Two open items I am carrying: the Tyro merchant credentials, and the offline question on the queue screen. Both are in Jira as risks with my name on them.

If you are blocked, say so the same day. Do not sit on it until standup. Thanks everyone."

# Stakeholder Management Notes:

## Stakeholder Communication Plan

| Stakeholder | What they need | Frequency | Channel | Owner |
| --- | --- | --- | --- | --- |
| Café owner | Progress against goal, scope and cost decisions | Bi-weekly | Sprint review in the shop | BA |
| Baristas / shift staff | Usability of the till, training on changes | Per sprint | Hands-on session before open | BA |
| Regular customers | Whether the queue got faster | Per release | In-store feedback card | BA |
| Coffee supplier | Stock data format, if CS-005 goes ahead | Ad hoc | Email | BA |
| Developers | Clarified acceptance criteria, unblocking | Daily | Standup / Jira | Tech Lead |
| Tester | Acceptance criteria and edge cases | Per story | Jira comments | BA |
| Bookkeeper | Receipt and GST format compliance | Once, before release | Email review | BA |

The barista row is the one that matters most and gets forgotten most. They are the daily users and they have no say in the budget, which means nobody asks them anything unless the BA goes and does it. Best time to catch them is the quiet stretch between 2pm and 3pm.

## Managing Expectations — Key Principles

- Under-promise on scope. 26 points against a 30-point capacity, not 30 against 30.

- Keep the board honest. If a card sits in In Progress for five days, move it or explain it. A tidy board that lies is worse than a messy one.

- Escalate blockers the day they appear. The Tyro credentials are a live example. Raised in week 1, that is a small change of plan; raised in week 2, it is a missed sprint goal.

- Demo on real hardware. Working software on the actual till, in the actual shop, at least every two weeks.

- Write down every scope decision. The CS-005 deferral above is recorded with its reasoning so it does not resurface as an argument later.

- Say no in the room, not by silence. The owner asked for table-service ordering during discovery. It was declined on the spot with a reason, which she accepted. Unanswered requests turn into assumptions.

# Product Backlog Management Tips

- Refinement. One hour mid-sprint, usually Wednesday of week 1, to groom the next sprint’s stories. Anything unrefined does not enter planning.

- Estimation. Planning Poker on the Fibonacci scale (1, 2, 3, 5, 8, 13). Anything estimated at 13 gets split before it enters a sprint. CS-008 is the example in this backlog.

- Dependencies. Map them before planning, not during. CS-001 depends on CS-004. CS-003 depends on CS-002. That chain is why the sprint order is what it is.

- Velocity. Track completed points per sprint. Three sprints of data before the number means anything.

- New ideas go to the bottom of the backlog, not into the current sprint. They get prioritised at the next refinement.

# If You Are Recording the Session

- Run it at 15 minutes, not 12 and not 20. The timing is part of what is being marked.

- Read the script out loud once before you record. The pauses marked [Wait for team response] need to sound like real pauses, around 3 to 5 seconds, even if nobody is there.

- Screen-share the Jira board while you talk and drag the four cards into the sprint on camera. That single action proves the backlog exists.

- Have a friend play the Dev Lead for the minute 5–8 section if you can. Push back on your 8-point estimate for CS-001. A planning session where nobody disagrees does not look like a planning session.

- Screenshot the board before and after, one showing the full backlog and one showing Sprint 1 committed, and put both in your submission.